## High Level Project Plan
Weeks
SAP REA
Week count | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7
 | time axis 2014-06-16 to 2014-08-03
Project Kick Off | bar: 2014-06-16
Requirements Phase | bar: 2014-06-17 to 2014-06-22
UI Phase | bar: 2014-06-23 to 2014-06-29
Development Phase | bar: 2014-06-30 to 2014-07-23
Testing Phase | bar: 2014-07-24 to 2014-07-29
Implementation and Deployment Phase | bar: 2014-07-28 to 2014-07-31

## Detail Level Plan
Weeks
SAP REA
Week Count
Saudi Holiday
Indian Holiday
 | time axis 2014-06-16 to 2014-08-03
Project Kick Off | bar: 2014-06-16
Requirements Phase | Requirements Gathering (BRD and Wireframes) | bar: 2014-06-17 to 2014-06-20
Peer Review | bar: 2014-06-21
Requirements Approval | bar: 2014-06-22
UI Phase | UI Design (iPhone and iPad) | bar: 2014-06-23 to 2014-06-24
UI Design (iPhone and iPad) peer review | bar: 2014-06-25
UI Design (Android) | bar: 2014-06-25 to 2014-06-26
UI Design (Android) peer review | bar: 2014-06-27
UI Design Approval | bar: 2014-06-29
Development Phase | Development of Mobile middleware | bar: 2014-06-30 to 2014-07-08
Development of Front End | bar: 2014-07-09 to 2014-07-21
Integration with CORVI | bar: 2014-07-22 to 2014-07-23
Testiing Phase | Testing and Bug Fixing | bar: 2014-07-24 to 2014-07-25
UAT | bar: 2014-07-27
Bug Fixing | bar: 2014-07-28 to 2014-07-29
Implementation and Deployment Phase | App store preparation for Freight Tracker | bar: 2014-07-28
Web server hosting prepartion for Freight Updater | bar: 2014-07-29
App store submission for Freight Tracker | bar: 2014-07-30 to 2014-07-31
Upload Freight Updater to web server | bar: 2014-07-30 to 2014-07-31
Project Closing | TBD