## Slide 1
Project Initiation Meeting:
Mobile Freight Tracking Experience
2014-JUN-16

## Slide 2
Project Description
Scope
Team Organization
Major Deliverables
Project Plan
Scheduled Activities
Expected Contributions by Stakeholder
Communications Plan
Change Management Plan
Next Steps
Agenda

## Slide 3
Project Description
Development of Mobile Freight Tracking Experience(MFTE)
Key Components of MFTE includes:
    Freight Tracker - Customer app
    Freight Updater - Vendor app
    Mobile Middleware

## Slide 4: Scope
Freight Tracker - Customer app | Freight Updater - Vendor app | Mobile Middleware
Freight tracking through mobile | Update freight status | connect Freight Tracker and Freight Updater to back end (CORVI)
Freight order history | Vendor View | 
Quick call |  | 
    Provide access to CORVI backend.
Kale Logistics scope
Motion 9 Studios Scope

## Slide 5: Team Organization
Mash Logistics
Role | Name
Business Sponsor | Director of Mash Logistics with Top Management
Business SME and CORVI Coordinator | Arfeen Ahmed (District Manager and CORVI coordinator)
Motion 9 Studios
Role | Name
Project Manager | Fathima Thotathil
Project Coordinator | Suhail Khan
Design and Development Lead | Mahesh Premayogan
Kale Logistics
Role | Name
CORVI Consultant | Nitin Master

## Slide 6: Major Deliverables
Phase | Description | Deliverable
Requirements Phase | Elicit and document requirements | Business Requirement Document (BRD) with Wireframes
UI Phase | Design and Finalize User Interface Design | UI Design for Freight Tracker and Freight Updater
Development Phase | Develop code for Freight Tracker and Freight Updater | Code
Acceptance and Handover | User Acceptance Testing and Handover mobile applications | Freight Tracker and Freight Updater

## Slide 7: Project Plan
Note : 7 weeks translate to 30 Business days.
Corvi Web API development to be completed
.

## Slide 8
Scheduled Activities
Requirements Phase
    Requirement elicitation meetings with Arfeen Ahmed
    Review BRD and Wireframes by Arfeen Ahmed
    Final Review and Approval by Arfeen Ahmed
    Share Approved BRD with Kale Logistics
UI Phase
    Review UI Design by Arfeen Ahmed
    Final Review and Approval by Arfeen Ahmed
Testing Phase
    User Acceptance Testing by Mash Logistics
Handover (Assumptions)
    Submit Freight Tracker to app store and google play store for review.
    Host Freight Updater to Mash Logistics Web server to download for vendors.

## Slide 9: Expected Contribution by Stakeholders
Mash Logistics
    Review and provide approvals for BRD and wireframes
    Review and provide approvals for UI Design
    User Acceptance Testing of proposed mobile apps
  Kale Logistics
    Provide access to CORVI backend

## Slide 10: Communications Plan
Communication Type | Medium | Frequency | Audience | Deliverables
Requirements elicitation meeting | Skype call | As needed | Project Manager SME | BRD and Wireframe sent in email
CORVI meeting | Skype call | Weekly | Project Manager CORVI coordinator Kale Logistics(Nitin) | API documentation by Kale Logistics
Weekly status reports | Email | Weekly | Project Manager | Project Status Report

## Slide 11: Change Management Plan
  Change Control Process
    Requirement has been Identified which is not part of SOW
    Motion 9 Studios will create a change request.
    Motion 9 Studios will provide time and cost estimates for the delivery of the Requirement
    Mash Logistics can Approve or Reject the changes
    If the Change is approved, this would be included in the project scope.

## Slide 12: Next Steps
  Requirements Elicitation
    Requirements Elicitation Meeting with Arfeen Ahmed on 18/6/2014.